## user stories
User story ID | As a | I want to | So that | Task
game manager | player | know when the level is finished | I know that I reached the goal of the level | 1. to implement a game manager
2.game manager(level loader)
3.game manager(input)
camera | player | see the game world as a character in the game | I can interact with the game | 1.to implement the camera class
2.camera(movement)
renderer | player | see the game world and is not empty or black screen | I can view the game world as intended | 1.to implement the render class
2.start the shader class/framework
menu | player | pause the game | I can do important thing outside the game without worrying to lose | 1.interagate the menu class to game manager
2.to implement a pause system/function
3.to implement a start game and exit game
input | player | interact with the world | I can move around and do stuff in the game | 1.to implement input class
2.interagate to game manager
movement | player | move around the game | I can go to different parts of the game | 1.to implement the movement method
2.registering input to the movement
HUD | player | to know the status of my player/ character | I can adjuct my gameplay accordingly | 1.to implement a HUD (renderer and camera class)
game object | player | move object | I can access new areas | 1.to implement game object
2.to inherit from game object for object
3.to inherit from game object for character
4.to inherit from character for enemy/NPC/player
collision | player | have a realistic or appropriate reponse from the game | the game felt like interaction is make according to the player action | 1.to implemet collision
2.collision for game object
character (enemy/npc) | player | have other entity to interact with in the game like enemy or NPC | the game is not empty level with no entity | 1.further expand character class
enemy AI | player | have the enemies to respond to my action | I can see them as a threat | 1.to implement state machine
2.chasing state
3.patrol state
4.Nav mesh navigation
player attack | player | be able to attack the enemy | I can proceed without danger | 1.to further expand player class attack

## Project Planner
Project Planner
[5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
design game concept | PLAN START | Number of day | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 2018-11-02 | in between 3 / 11 / 2018 and 16/ 01/2019(75days) | [72 empty] | 2018-01-16
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75
Design game concept | 1 | 1 | 1 | 1 | 100%
to implement Game manager | 2 | 5 | 2 | 5 | 0% | bar: in between 3 / 11 / 2018 and 16/ 01/2019(75days) 2 to in between 3 / 11 / 2018 and 16/ 01/2019(75days) 6
game manager (level loader) | 2 | 4 | 2 | 4 | 0% | bar: in between 3 / 11 / 2018 and 16/ 01/2019(75days) 2 to in between 3 / 11 / 2018 and 16/ 01/2019(75days) 6
game manager (input) | 6 | 1 | 6 | 1 | 0% | bar: in between 3 / 11 / 2018 and 16/ 01/2019(75days) 2 to in between 3 / 11 / 2018 and 16/ 01/2019(75days) 6
to implement develop Camera | 7 | 3 | 7 | 3 | 0% | bar: in between 3 / 11 / 2018 and 16/ 01/2019(75days) 2 to in between 3 / 11 / 2018 and 16/ 01/2019(75days) 6
camera (movement) | 8 | 2 | 8 | 2 | 0% | bar: in between 3 / 11 / 2018 and 16/ 01/2019(75days) 2 to in between 3 / 11 / 2018 and 16/ 01/2019(75days) 6
to implement develop Renderer | 10 | 3 | 10 | 3 | 0% | bar: in between 3 / 11 / 2018 and 16/ 01/2019(75days) 2 to in between 3 / 11 / 2018 and 16/ 01/2019(75days) 6
start the shader class/framemwork | 12 | 1 | 12 | 1 | 0% | bar: in between 3 / 11 / 2018 and 16/ 01/2019(75days) 2 to in between 3 / 11 / 2018 and 16/ 01/2019(75days) 6
interagete the menu class to game manager | 13 | 6 | 13 | 6 | 0% | bar: in between 3 / 11 / 2018 and 16/ 01/2019(75days) 2 to in between 3 / 11 / 2018 and 16/ 01/2019(75days) 6
to implement a pause system/function | 13 | 3 | 13 | 3 | 0%
to implement a start game and exit game | 16 | 3 | 16 | 3 | 0%
to implement input class | 19 | 2 | 19 | 2 | 0%
interagate to game manager | 20 | 1 | 20 | 1 | 0%
to implement the movement method | 21 | 3 | 21 | 3 | 0%
registering input to the movement | 23 | 1 | 23 | 1 | 0%
to implement a HUD (renderer and camera class) | 24 | 3 | 24 | 3 | 0% | bar: 2018-11-02 1 to in between 3 / 11 / 2018 and 16/ 01/2019(75days) 10
to implement game object | 27 | 9 | 27 | 9 | 0% | bar: 2018-11-02 1 to in between 3 / 11 / 2018 and 16/ 01/2019(75days) 10
to inherit from game object for object | 27 | 3 | 27 | 3 | 0%
to inherit from game object for character | 30 | 3 | 30 | 3 | 0%
to inherit from character for enemy/NPC/player | 33 | 3 | 33 | 3 | 0%
to implemet collision | 36 | 9 | 36 | 9 | 0%
collision for game object | 39 | 6 | 39 | 6 | 0%
planned testing 1 | 45 | 2 | 45 | 2 | 0%
further expand character class | 47 | 2 | 47 | 2 | 0%
to implement state machine | 49 | 9 | 49 | 9 | 0%
chasing state | 52 | 3 | 52 | 3 | 0%
patrol state | 55 | 3 | 55 | 3 | 0%
Nav mesh navigation | 58 | 3 | 58 | 3 | 0%
planned Testing phase 2 | 59 | 2 | 59 | 2 | 0%
to further expand player class (attack) | 61 | 3 | 61 | 3 | 0%
extra time to finish the game | 64 | 8 | 64 | 8 | 0%
planned Final testing | 72 | 2 | 72 | 2 | 0%
planned Report | 74 | 2 | 74 | 2 | 0% | bar: in between 3 / 11 / 2018 and 16/ 01/2019(75days) 74 to 2018-01-16 75
time duration | [5 empty] | 2018-11-02 1: start | deadlines