## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
design game concept | PLAN START | Number of day | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 2018-10-26 | [73 empty] | 2018-01-09 | [6 empty] | 2018-01-16
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82
Design game concept | 1 | 1 | 1 | 1 | 100%
planned develop Game manager | 2 | 3 | 2 | 3 | 0% | bar: 2018-10-26 2 to 2018-10-26 6
planned develop Camera | 3 | 4 | 3 | 4 | 0% | bar: 2018-10-26 2 to 2018-10-26 6
planned develop Renderer | 3 | 4 | 3 | 4 | 0% | bar: 2018-10-26 2 to 2018-10-26 6
planned develop Start menu | 6 | 1 | 6 | 1 | 0% | bar: 2018-10-26 2 to 2018-10-26 6
planned develop Input | 7 | 1 | 7 | 1 | 0%
planned develop Game Object | 8 | 4 | 8 | 4 | 0%
planned develop Object | 9 | 4 | 9 | 4 | 0%
planned develop Level | 10 | 4 | 10 | 4 | 0%
planned develop HUD | 11 | 4 | 11 | 4 | 0%
planned develop Character | 15 | 4 | 15 | 4 | 0%
planned develop State machine/basic AI | 19 | 4 | 19 | 4 | 0%
planned testing 1 | 23 | 2 | 23 | 2 | 0%
planned further develop game manager | 25 | 7 | 25 | 7 | 0%
planned furthur develop Character | 32 | 4 | 32 | 4 | 0%
planned develop Collision | 36 | 7 | 36 | 7 | 0%
planned Testing phase 2 | 43 | 7 | 43 | 7 | 0%
planned finish develop Game manager | 50 | 21 | 50 | 21 | 0%
planned Final testing | 71 | 3 | 71 | 3 | 0%
planned Report | 74 | 2 | 74 | 2 | 0%
time duration | [5 empty] | 2018-10-26 1: start; 2018-01-09 75: deadlines; 2018-01-09 77: extended new deadlines